## About
TWYNTRUST FRAMEWORK · Quillfen Studio
Integrated Risk Register and Treatment Plan
Quillfen Studio's single register for information-security and AI risks, with the treatment plan, the scales and a live heat map. Built with the method in IMS-PRO-001.
Document ID | IMS-REG-002
Version | 2.0
Prepared by | Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai
License | CC BY 4.0 — free to share and adapt, including commercially, with credit to Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai · creativecommons.org/licenses/by/4.0
Classification | Internal
Owner | [Security Lead]
Approved by | [CEO] (Trust Council)
Effective date | 2026-11-01
Kit folder | 02 Gauge - Risk and Planning
ISO/IEC 27001:2022 | 6.1.2, 6.1.3, 8.2, 8.3; Annex A referenced per risk
ISO/IEC 42001:2023 | 6.1.2, 6.1.3, 8.2, 8.3; Annex A referenced per risk; inputs from 6.1.4 / 8.4
How to use this workbook
• | This is a SAMPLE filled in for the example company Quillfen Studio. Keep the structure, replace the example rows with your own.
• | Yellow cells are fill-in fields. Drop-down cells only accept the listed values.
• | Cells with formulas (scores, levels, due status) calculate automatically — do not type over them.
• | Enter likelihood and impact as numbers 1–5. Score and level columns calculate themselves.
• | Every risk needs one named owner. Residual High risks need Trust Council acceptance (see IMS-PRO-001 section 9).
• | Write Annex A references in both control columns when a risk needs controls from both standards — then copy them into the two Statements of Applicability (IMS-SOA-001, IMS-SOA-002).
• | Save a dated copy every quarter so auditors can see how risks changed over time.
Sheets
Risk Register | One row per risk. Scales are on the 'Scales' sheet; method in IMS-PRO-001 Risk Management Methodology (Information Security and AI). IS = information-security risk, AI = AI risk. Inherent = with today's controls; residual = after planned controls work.
Treatment Plan | Actions that put the planned controls in place. Each action belongs to a risk. 'Due status' calculates itself from the due date and status.
Scales | The same scales are used in IMS-PRO-001 Risk Management Methodology (Information Security and AI) and IMS-PRO-002 AI System Impact Assessment Procedure and Worked Example. Change them only by Trust Council decision, and everywhere at once.
Heat map | Counts of risks per likelihood × impact cell, calculated from the Risk Register with COUNTIFS. Compare the inherent and residual grids to show the effect of treatment.

## Risk Register
Integrated Risk Register (Information Security + AI)
One row per risk. Scales are on the 'Scales' sheet; method in IMS-PRO-001 Risk Management Methodology (Information Security and AI). IS = information-security risk, AI = AI risk. Inherent = with today's controls; residual = after planned controls work.
Risk ID | Type | Risk title | Cause (threat / vulnerability / source) | Consequence | Affected system / asset | Risk owner | Inherent L | Inherent I | Inherent score | Inherent level | Existing controls | Treatment option | Planned controls — 27001 Annex A | Planned controls — 42001 Annex A | Residual L | Residual I | Residual score | Residual level | Accepted by | Next review | Status
RSK-AI-001 | AI | StoryFrame fine-tuning set contains artwork without valid consent or licence | Bulk-licensed image packs and early commissions without a per-image consent record; artist opt-outs not propagated to the training set | Copyright claims, artists' trust lost, model must be retrained; breach of Artist Agreement | AI-SYS-001 StoryFrame | [Data and ML Lead] | 4 | 4 |  |  | Licence checks on new packs; consent ledger for commissions since 2025 | Modify | 5.32 | A.7.3, A.7.5, A.4.3 | 2 | 4 |  |  | [Data and ML Lead] (risk owner) | 2027-01-15 | In progress
RSK-AI-002 | AI | Prompt or filter bypass lets StoryFrame produce a deceptive deepfake of a real person | Prompts naming real people or jailbreak phrasing get past the content filter | Deceptive image harms a real person's reputation; EU AI Act deepfake duties breached; customer trust lost | AI-SYS-001 StoryFrame | [Head of AI] | 3 | 5 |  |  | SafeFrame screening; visible AI label; C2PA content credentials | Modify | 8.16 | A.6.2.4, A.6.2.6, A.10.3 | 2 | 4 |  |  | [Head of AI] (reported to Trust Council) | 2027-03-31 | In progress
RSK-AI-003 | AI | ArtistMatch ranking systematically under-exposes new or non-English-portfolio artists | Ranking features weight rating history and English-language tags heavily | New and non-English-portfolio artists get fewer commissions and less income; unfair outcome | AI-SYS-003 ArtistMatch | [Head of AI] | 4 | 3 |  |  | Manual monthly fairness review of exposure ratio | Modify | — | A.5.2–A.5.4, A.6.2.4, A.8.2 | 2 | 3 |  |  | [Head of AI] (risk owner) | 2027-01-15 | In progress
RSK-AI-004 | AI | ScriptMate hallucinates scenes or leaks one customer's script into another's session | Model confabulates scenes; session context bug or shared cache mixes customers' scripts | Wrong storyboards delivered; confidential unreleased script disclosed to another customer | AI-SYS-002 ScriptMate | [Head of AI] | 3 | 4 |  |  | Zero-retention API terms; per-tenant session isolation; user can edit scene list | Modify | 8.11, 8.26 | A.6.2.4, A.9.3 | 1 | 4 |  |  | [Head of AI] (risk owner) | 2027-03-31 | Implemented
RSK-AI-005 | AI | SafeFrame vendor model update silently lowers detection of prohibited content | Vendor ships model updates without notice; we did not pin versions or re-test after changes | Prohibited or deceptive content reaches customers; harm to depicted people; regulatory exposure | AI-SYS-004 SafeFrame | [Creative Director] | 3 | 5 |  |  | Weekly canary test set; vendor version pinning (since INC-2026-007) | Modify | 5.22 | A.10.3, A.6.2.6 | 2 | 5 |  |  | Trust Council 2026-10-21, until 2027-01-31, pending CA-2026-004 | 2027-01-31 | In progress
RSK-IS-001 | IS | Unreleased customer scripts exposed through a misconfigured storage bucket | Bucket policy changed by hand outside infrastructure-as-code; no public-access guard | Unreleased customer scripts exposed; notifiable breach; contract penalties | AST-004 Customer scripts, prompts and project files | [Platform Engineer] | 3 | 4 |  |  | Encryption at rest; IaC for most buckets | Modify | 8.9, 8.12, 8.15, 5.23 | — | 1 | 4 |  |  | [Platform Engineer] (risk owner) | 2027-03-31 | Implemented
RSK-IS-002 | IS | Account takeover of an engineer through phishing leads to production access | Credential phishing with relayed one-time codes against engineers | Attacker reaches production; customer data and model weights stolen; notifiable breach | AST-010 Staff identities, SSO and company laptops | [Security Lead] | 3 | 5 |  |  | SSO with app-based one-time codes; yearly awareness training | Modify | 5.17, 8.2, 8.5, 6.3 | — | 1 | 5 |  |  | [Security Lead] (risk owner) | 2027-03-31 | Implemented
RSK-IS-003 | IS | Secrets or source code pasted into unapproved AI tools by staff | Staff use free AI chatbots to debug code or summarise documents | Source code, API keys or customer data disclosed to an AI vendor and possibly used for training | AST-009 Company source code repositories | [Security Lead] | 4 | 3 |  |  | Acceptable use guidance (informal); secret scanning in CI | Modify | 5.10, 6.3, 8.12 | A.9.2, A.9.4 | 2 | 3 |  |  | [Security Lead] (risk owner) | 2027-01-15 | In progress
RSK-IS-004 | IS | Loss of the primary cloud region stops Canvas and the API for more than a day | Single-region deployment; restore process untested | Canvas and API down for more than 24 hours; SLA credits; customers leave | AST-001 Production cloud environment (AWS accounts, eu-west-1 and me-central-1) | [Platform Engineer] | 2 | 4 |  |  | Daily snapshots; multi-AZ database | Modify | 5.29, 5.30, 8.13, 8.14 | — | 2 | 2 |  |  | [Platform Engineer] (risk owner) | 2027-03-31 | Implemented
RSK-IS-005 | IS | Vulnerable open-source dependency exploited in the Canvas web app | Outdated npm packages; no time-bound patching rule | Remote code execution or data theft through the web app | AST-002 Quillfen Canvas web application and its source code | [CTO] | 3 | 4 |  |  | Dependency scanning alerts in GitHub | Modify | 8.8, 8.25, 8.28, 8.29 | — | 2 | 3 |  |  | [CTO] (risk owner) | 2027-01-15 | In progress
RSK-IS-006 | IS | Former contractor keeps access to GitHub or AWS after the contract ends | Contractor offboarding run by hiring managers; no automatic deprovisioning | Source code or customer data accessed by someone with no business need | AST-010 Staff identities, SSO and company laptops | [Security Lead] | 3 | 3 |  |  | Enterprise SSO for most tools | Modify | 5.11, 5.18, 6.5 | — | 1 | 3 |  |  | [Security Lead] (risk owner) | 2027-03-31 | In progress
RSK-IS-007 | IS | Ransomware on a company laptop encrypts synced business records | Malicious attachment; sync client propagates encrypted files | Finance and HR records unavailable for days; possible personal-data breach | AST-011 Business records (finance, HR, contracts) | [Security Lead] | 2 | 3 |  |  | EDR on all laptops; SaaS version history | Modify | 8.1, 8.7, 8.13 | — | 1 | 3 |  |  | [Security Lead] (risk owner) | 2027-03-31 | Implemented
RSK-IS-008 | IS | Foundation-model API key leaked and abused | Key committed to a repository or pasted into a ticket; no spend limit | Five-figure bill overnight; prompts and outputs exposed; service suspended by provider | AST-008 Foundation-model and image-model API keys and service accounts | [Platform Engineer] | 3 | 4 |  |  | Secrets manager for production; secret scanning in CI | Modify | 5.17, 8.12, 8.16, 8.24 | A.4.4 | 2 | 3 |  |  | [Platform Engineer] (risk owner) | 2027-01-15 | In progress
RSK-IS-009 | IS | Broken access control in Commons exposes artists' payout and identity details | Object IDs in the API not checked against the logged-in user | Personal data of artists exposed; notifiable breach; artists leave the marketplace | AST-003 Quillfen Commons marketplace (artist profiles, commissions, payouts data) | [CTO] | 3 | 4 |  |  | Code review; annual pentest | Modify | 8.3, 8.26, 8.28, 8.29 | — | 1 | 4 |  |  | [CTO] (risk owner) | 2027-03-31 | Implemented
RSK-AI-006 | AI | Prompt injection hidden in an uploaded script makes ScriptMate ignore its instructions | Untrusted script text passed to the model in the same context as system instructions | Misleading scene lists; system prompt disclosed; customer loses trust | AI-SYS-002 ScriptMate | [Head of AI] | 3 | 3 |  |  | Output limited to scene lists; no tool access | Modify | 8.28 | A.6.2.4, A.6.2.6 | 2 | 2 |  |  | [Head of AI] (risk owner) | 2027-03-31 | In progress
RSK-AI-007 | AI | StoryFrame outputs closely imitate a living artist's signature style or a protected character | Base model memorised popular works; prompts name living artists | Infringement claim; harm to the artist's income and reputation; marketplace trust lost | AI-SYS-001 StoryFrame | [Creative Director] | 3 | 4 |  |  | Artist-name prompt warnings | Modify | 5.32 | A.6.2.4, A.7.5, A.8.2, A.9.4 | 2 | 3 |  |  | [Creative Director] (risk owner) | 2027-01-15 | In progress
RSK-AI-008 | AI | ArtistMatch relevance drifts as the marketplace grows and nobody notices | Model trained on 2025 data; no drift metric or alert | Poor matches, fewer completed commissions, unfair exposure creeping back | AI-SYS-003 ArtistMatch | [Data and ML Lead] | 3 | 2 |  |  | Quarterly manual retrain | Modify | — | A.6.2.6, A.6.2.8 | 2 | 2 |  |  | [Data and ML Lead] (risk owner) | 2027-03-31 | Planned
RSK-AI-009 | AI | Engineers accept insecure CodeAssist suggestions without proper review | Over-trust in AI suggestions; time pressure; reviewers assume code was checked | Vulnerabilities shipped to production | AI-SYS-005 CodeAssist | [CTO] | 4 | 3 |  |  | Mandatory code review; SAST in CI | Modify | 8.25, 8.28, 8.29 | A.9.2, A.9.3 | 2 | 3 |  |  | [CTO] (risk owner) | 2027-03-31 | In progress
RSK-AI-010 | AI | Customers publish StoryFrame images in adverts without the required AI disclosure | Customers strip labels or credentials; terms do not explain their duties | Audiences deceived; customer and our brand exposed under EU AI Act and advertising rules | AI-SYS-001 StoryFrame | [Privacy and Legal Lead] | 3 | 3 |  |  | Visible label and C2PA credentials on export | Share | 5.31 | A.8.2, A.9.4, A.10.4 | 2 | 3 |  |  | [Privacy and Legal Lead] (risk owner) | 2027-03-31 | Planned
[RSK-IS-0xx] | [IS or AI] | [cause → event → consequence in one line] | [cause] | [who or what is harmed] | [AST-0xx or AI-SYS-00x] | [one named owner] |  |  |  |  | [controls that work today] |  | [e.g. 8.8] | [e.g. A.6.2.4] |  |  |  |  | [name, date] | [yyyy-mm-dd] | Open

## Treatment Plan
Risk Treatment Plan
Actions that put the planned controls in place. Each action belongs to a risk. 'Due status' calculates itself from the due date and status.
Action ID | Risk ID | Action | Owner | Control refs (27001; 42001) | Due date | Status | Due status | Evidence
TP-01 | RSK-AI-001 | Audit every image in the fine-tuning set against the consent ledger; remove unverified images and retrain | [Data and ML Lead] | 5.32; A.7.3, A.7.5, A.4.3 | 2026-09-30 | In progress |  | Audit report; dataset hash before/after
TP-02 | RSK-AI-001 | Automate opt-out propagation from Commons profile to the training-data exclusion list | [Data and ML Lead] | 5.32; A.7.3, A.7.5, A.4.3 | 2026-12-15 | In progress |  | Pipeline run log; test opt-out record
TP-03 | RSK-AI-002 | Add named-person likeness check before image delivery | [Head of AI] | 8.16; A.6.2.4, A.6.2.6, A.10.3 | 2026-08-31 | Done |  | Release record; red-team rerun 0/200 bypasses
TP-04 | RSK-AI-002 | Quarterly red-team of deepfake prompts with Artist Advisory Panel member | [Head of AI] | 8.16; A.6.2.4, A.6.2.6, A.10.3 | 2026-12-31 | In progress |  | Red-team reports
TP-05 | RSK-AI-003 | Add exposure-boost slot for new artists and automatic alert when ratio < 0.8 | [Head of AI] | A.5.2–A.5.4, A.6.2.4, A.8.2 | 2026-11-30 | In progress |  | Model card update; alert config (OFI-2026-05)
TP-06 | RSK-AI-005 | CA-2026-004: model-change notice and version-pinning clause in SafeFrame agreement and AI supplier template | [Privacy and Legal Lead] | 5.22; A.10.3, A.6.2.6 | 2026-11-30 | In progress |  | Signed contract amendment
TP-07 | RSK-AI-005 | Run canary test set daily for 30 days after INC-2026-007, then weekly with alerting | [Creative Director] | 5.22; A.10.3, A.6.2.6 | 2026-09-15 | Done |  | Canary dashboard export
TP-08 | RSK-IS-001 | Account-level public-access block and IaC drift detection on all buckets | [Platform Engineer] | 8.9, 8.12, 8.15, 5.23 | 2026-06-30 | Done |  | Cloud config screenshot; CI policy check
TP-09 | RSK-IS-002 | Roll out passkeys / security keys to all staff and contractors | [Security Lead] | 5.17, 8.2, 8.5, 6.3 | 2026-07-31 | Done |  | Identity provider MFA report: 100% phishing-resistant
TP-10 | RSK-IS-002 | Just-in-time production access with approval and 4-hour expiry | [Security Lead] | 5.17, 8.2, 8.5, 6.3 | 2026-08-31 | Done |  | Access request log
TP-11 | RSK-IS-003 | Publish generative-AI rules in the Acceptable Use Policy and block unapproved AI tools on managed laptops | [Security Lead] | 5.10, 6.3, 8.12; A.9.2, A.9.4 | 2026-10-31 | In progress |  | IMS-POL-005 v2; web-filter rule
TP-12 | RSK-IS-005 | Patch SLA in CI: build fails on critical vulnerabilities older than 7 days | [CTO] | 8.8, 8.25, 8.28, 8.29 | 2026-10-15 | In progress |  | CI policy; vulnerability age report
TP-13 | RSK-IS-006 | Route all contractor onboarding/offboarding through People Ops with automatic deprovisioning (see CA-2026-005) | [People and Operations Lead] | 5.11, 5.18, 6.5 | 2026-10-31 | In progress |  | Checklist; SSO deprovision log
TP-14 | RSK-IS-008 | Set spend limits and anomaly alerts on all model-provider accounts | [Platform Engineer] | 5.17, 8.12, 8.16, 8.24; A.4.4 | 2026-09-30 | In progress |  | Provider console settings
TP-15 | RSK-AI-008 | Add drift metric (population stability index) to monthly ArtistMatch report | [Data and ML Lead] | A.6.2.6, A.6.2.8 | 2027-01-31 | Not started |  | Monitoring dashboard
TP-16 | RSK-AI-010 | Update customer terms with AI-disclosure duties and in-app reminder at export | [Privacy and Legal Lead] | 5.31; A.8.2, A.9.4, A.10.4 | 2026-12-31 | Not started |  | Terms v4; UI release note
[TP-xx] | [RSK-..] | [what will be done] | [owner] | [Annex A refs] | [due date] | Not started |  | [where the proof will be]
Formulas:
Due status = IF([Due date]="","",IF([Status]="Done","Done",IF([Due date]<TODAY(),"Overdue","On track")))

## Scales
Risk scales and treatment options
The same scales are used in IMS-PRO-001 Risk Management Methodology (Information Security and AI) and IMS-PRO-002 AI System Impact Assessment Procedure and Worked Example. Change them only by Trust Council decision, and everywhere at once.
Scale | Value | Name | Meaning
Likelihood (L)
Likelihood | 1 | Rare | Not expected in the next 3 years
Likelihood | 2 | Unlikely | Could happen once in 2–3 years
Likelihood | 3 | Possible | Could happen about once a year
Likelihood | 4 | Likely | Expected several times a year
Likelihood | 5 | Almost certain | Expected monthly or already happening
Impact (I)
Impact | 1 | Negligible | No harm to people; cost < USD 5k; nobody outside notices
Impact | 2 | Minor | Short inconvenience for a few users or artists; < USD 25k; one customer complaint
Impact | 3 | Moderate | Noticeable harm, unfair outcome or data exposure for a limited group; < USD 100k; a customer escalates or a regulator asks questions
Impact | 4 | Major | Serious harm to people or rights, notifiable data breach, IP infringement claim; < USD 500k; loss of a key customer
Impact | 5 | Severe | Harm to a vulnerable person, widespread unfair or deceptive outcomes, or > USD 500k; threatens the company's survival or market access
Risk level (score = L × I)
Level | 1–4 | Low | Accept; risk owner monitors
Level | 5–9 | Medium | Treat, or accept by the risk owner; review every 6 months
Level | 10–15 | High | Must treat; residual acceptance only by the Security Lead or Head of AI plus the Trust Council
Level | 16–25 | Critical | Not acceptable; stop, redesign or withdraw; tell the CEO within 24 hours
Treatment options
Treatment |  | Modify | Add or improve controls to reduce likelihood or impact
Treatment |  | Avoid | Stop or change the activity that creates the risk
Treatment |  | Share | Transfer part of the impact by contract, insurance or supplier
Treatment |  | Retain | Accept as it is, within the acceptance rules in IMS-PRO-001

## Heat map
Risk heat map (calculated)
Counts of risks per likelihood × impact cell, calculated from the Risk Register with COUNTIFS. Compare the inherent and residual grids to show the effect of treatment.
Likelihood ↓ / Impact → | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Severe | Total
INHERENT RISK — number of risks in each cell
5 Almost certain
4 Likely
3 Possible
2 Unlikely
1 Rare
Total
RESIDUAL RISK — number of risks in each cell
5 Almost certain
4 Likely
3 Possible
2 Unlikely
1 Rare
Total
RISK LEVEL OF EACH CELL (key)
5 Almost certain | Medium | High | High | Critical | Critical
4 Likely | Low | Medium | High | Critical | Critical
3 Possible | Low | Medium | Medium | High | High
2 Unlikely | Low | Low | Medium | Medium | High
1 Rare | Low | Low | Low | Low | Medium