## About
TWYNTRUST FRAMEWORK · Quillfen Studio
Objectives, Metrics and Monitoring Plan
Quillfen Studio's information-security and AI objectives with the plan to achieve them, the metrics used to monitor both management systems, and the calendar for measuring and reviewing them.
Document ID | IMS-REG-003
Version | 2.0
Prepared by | Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai
License | CC BY 4.0 — free to share and adapt, including commercially, with credit to Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai · creativecommons.org/licenses/by/4.0
Classification | Internal
Owner | [Compliance Coordinator]
Approved by | [CEO] (Trust Council)
Effective date | 2026-11-01
Kit folder | 02 Gauge - Risk and Planning
ISO/IEC 27001:2022 | 6.2, 9.1; supports 9.3 inputs
ISO/IEC 42001:2023 | 6.2, 9.1; Annex A.6.2.6 (operation and monitoring)
How to use this workbook
• | This is a SAMPLE filled in for the example company Quillfen Studio. Keep the structure, replace the example rows with your own.
• | Yellow cells are fill-in fields. Drop-down cells only accept the listed values.
• | Cells with formulas (scores, levels, due status) calculate automatically — do not type over them.
• | Keep objectives few (5–8) and measurable. Each one needs a plan: what, resources, who, when, how evaluated.
• | KPI = how well we are doing; KRI = an early warning that a risk is growing. Every High risk should have at least one KRI.
• | Update the 'Last value' column before each Trust Council meeting.
Sheets
Objectives | Objectives set by the Trust Council for both standards, with the planning details both standards ask for (what, resources, who, when, how results are evaluated).
Metrics | What we measure to know whether the integrated system and our AI systems work as intended, including AI performance, drift and fairness. Results feed the management review (IMS-PRO-008 Management Review Procedure and Example Minutes).
Monitoring Calendar | When each thing is measured or reviewed, by whom, what record it produces and where the result goes.

## Objectives
Objectives and plans to achieve them
Objectives set by the Trust Council for both standards, with the planning details both standards ask for (what, resources, who, when, how results are evaluated).
ID | Objective | Standard | Metric | Target | What will be done | Resources | Owner | When | How evaluated | Current value | Status
OBJ-01 | Certify the integrated system | Both | ISO/IEC 27001 and ISO/IEC 42001 certificates issued | Both by 2027-09-30 | Finish Stage 1 and Stage 2 audits for both standards with one certification body; close all audit nonconformities on time | Certification fee budget; 0.5 FTE Compliance Coordinator; external internal-audit support | [CEO] | Stage 1 2027-05; Stage 2 2027-07; certificates by 2027-09-30 | Milestones tracked monthly at the Trust Council | AUD-2026-02 done; 2 minor NCs open | On track
OBJ-02 | Every AI release passes the AI Release Review | 42001 | % of AI releases with an approved impact assessment and gate record | 100% | Every new or significantly changed AI system gets an AIIA and a AI Release Review record before release | AI Release Review members' time (≈ 4 h per release); AIIA template | [Head of AI] | Continuous; reported monthly | Release log checked against AIIA register each month; sampled in internal audit | 100% (3 of 3 AI releases in 2026) | Met
OBJ-03 | Respect artists' rights in training data | 42001 | % of fine-tuning images with a verified licence or consent record | 100%; zero unresolved opt-out requests older than 14 days | Image-by-image consent audit of the fine-tuning set; automatic opt-out propagation | 2 weeks of Data/ML engineering; consent ledger tooling | [Data and ML Lead] | Audit 2026-09-30; automation 2026-12-15 | Monthly data-provenance report; opt-out age report | 100% of the current set verified (41 unverified images removed); one opt-out took 17 days (INC-2026-009) | Not met
OBJ-04 | Keep critical vulnerabilities short-lived | 27001 | Median days to fix critical/high vulnerabilities in production | Critical ≤ 7 days, high ≤ 30 days | CI blocks builds with critical vulnerabilities older than 7 days; weekly triage | Dependency scanner (existing); 2 h/week engineering triage | [CTO] | From 2026-10-15 | Vulnerability age report from the scanner, monthly | Critical median 4 days; high median 34 days | Not met
OBJ-05 | Make people the strongest control | Both | Staff completing security + AI awareness training; phishing-simulation report rate | 100% within 30 days of joining and yearly; report rate ≥ 60% | Combined security + AI awareness module at onboarding and yearly; quarterly phishing simulation; contractor onboarding through People Ops (CA-2026-005) | Training platform licence; 1 h per person per year | [People and Operations Lead] | Ongoing; contractor fix by 2026-10-31 | Training platform completion report; phishing simulation report rate | 94% trained; report rate 63% | In progress
OBJ-06 | Fair exposure for artists | 42001 | ArtistMatch exposure ratio for new vs established artists (top-10 results) | ≥ 0.8 every month | Exposure-boost slot for new artists; automatic alert when the ArtistMatch ratio drops below 0.8 | 1 sprint of ML engineering; monitoring dashboard | [Head of AI] | Alert live by 2026-11-30 | Monthly fairness report reviewed by the Head of AI | Jun 0.83, Jul 0.79, Aug 0.84, Sep 0.86 (July below target) | Not met
OBJ-07 | Stay available | 27001 | Canvas and API monthly availability | ≥ 99.5% | Multi-AZ everywhere; quarterly restore test; tested regional failover runbook | Cloud budget +8%; SRE time | [Platform Engineer] | Failover test 2026-12 | Uptime monitor, monthly | Lowest month 99.6% (June); average 99.8% | Met
[OBJ-0x] | [what you want to achieve] | [27001 / 42001 / Both] | [how you measure it] | [target and date] | [actions] | [budget, people, tools] | [owner] | [when] | [how and how often you check] |  | Not started

## Metrics
Metrics — KPIs and KRIs
What we measure to know whether the integrated system and our AI systems work as intended, including AI performance, drift and fairness. Results feed the management review (IMS-PRO-008 Management Review Procedure and Example Minutes).
ID | Type | Standard | Metric | Linked objective / risk | Source | Frequency | Threshold / target | Owner | Last value | Last measured | Status
M-01 | KPI | 42001 | AI releases with approved AIIA and release-review record | OBJ-02 | Release log + AIIA register | Monthly | 100% | [Head of AI] | 100% | 2026-09-30 | Met
M-02 | KPI | 42001 | Fine-tuning images with verified licence or consent | OBJ-03; RSK-AI-001 | Consent ledger vs dataset manifest | Monthly | 100% | [Data and ML Lead] | 100% | 2026-09-30 | Met
M-03 | KRI | 42001 | Opt-out requests unresolved after 14 days | OBJ-03 | Commons opt-out queue | Weekly | 0 | [Data and ML Lead] | 1 (17 days, INC-2026-009) | 2026-09-30 | Not met
M-04 | KPI | 42001 | ArtistMatch exposure ratio, new vs established artists (top-10) | OBJ-06; RSK-AI-003 | Ranking logs, fairness notebook | Monthly | ≥ 0.8 | [Head of AI] | 0.86 (Sep); 0.79 in Jul | 2026-09-30 | Not met
M-05 | KRI | 42001 | ArtistMatch drift — population stability index of input features | RSK-AI-008 | Monitoring dashboard | Monthly | < 0.2 | [Data and ML Lead] | 0.12 | 2026-09-30 | Met
M-06 | KRI | 42001 | SafeFrame detection rate on canary test set (prohibited + real-person likeness) | RSK-AI-005; RSK-AI-002 | Canary test run | Weekly (daily after a vendor change) | ≥ 98% | [Creative Director] | 99.1% | 2026-09-30 | Met
M-07 | KRI | 42001 | StoryFrame deepfake red-team bypass rate | RSK-AI-002 | Red-team report | Quarterly | 0 of 200 attempts | [Head of AI] | 0 / 200 | 2026-09-30 | Met
M-08 | KPI | 42001 | ScriptMate scene-list accuracy on reference scripts (no invented scenes) | RSK-AI-004 | Evaluation suite in CI | Each release + monthly | ≥ 95% | [Data and ML Lead] | 96.4% | 2026-09-30 | Met
M-09 | KPI | 27001 | Median days to fix critical / high vulnerabilities in production | OBJ-04; RSK-IS-005 | Dependency and container scanner | Monthly | Critical ≤ 7; high ≤ 30 | [CTO] | 4 / 34 | 2026-09-30 | Not met
M-10 | KPI | Both | Staff and contractors trained within 30 days of joining and yearly | OBJ-05 | Training platform | Monthly | 100% | [People and Operations Lead] | 94% | 2026-09-30 | Not met
M-11 | KPI | 27001 | Phishing simulation report rate | OBJ-05; RSK-IS-002 | Phishing simulation tool | Quarterly | ≥ 60% | [People and Operations Lead] | 63% | 2026-09-30 | Met
M-12 | KPI | 27001 | Accounts with phishing-resistant MFA | RSK-IS-002 | Identity provider report | Monthly | 100% | [Security Lead] | 100% | 2026-09-30 | Met
M-13 | KPI | 27001 | Canvas and API availability | OBJ-07; RSK-IS-004 | Uptime monitor | Monthly | ≥ 99.5% | [Platform Engineer] | 99.71% | 2026-09-30 | Met
M-14 | KPI | 27001 | Successful restore tests | RSK-IS-004 | Restore test record | Quarterly | 1 per quarter, RTO ≤ 8 h | [Platform Engineer] | 1, 5.5 h | 2026-09-30 | Met
M-15 | KPI | Both | Access reviews completed for production, GitHub and model registry | RSK-IS-006 | Access review records | Quarterly | 100% on time | [Security Lead] | 2 of 3 | 2026-09-30 | Not met
M-16 | KRI | Both | Security and AI incidents rated S1/S2 | IMS-PRO-005 | Incident log | Monthly | 0 S1; ≤ 1 S2 per quarter | [Security Lead] | 1 S2 (INC-2026-007) | 2026-09-30 | Met
M-17 | KPI | Both | Corrective actions closed by due date | IMS-PRO-009 | CAPA log | Monthly | ≥ 90% | [Compliance Coordinator] | 2 open, 0 overdue | 2026-09-30 | On track
M-18 | KPI | Both | Critical suppliers (incl. AI model suppliers) reviewed in last 12 months | RSK-AI-005 | Supplier register | Quarterly | 100% | [Privacy and Legal Lead] | 80% | 2026-09-30 | Not met
[M-xx] | [KPI or KRI] | [27001 / 42001 / Both] | [what you count] | [OBJ / RSK] | [system or report] | [how often] | [target or tolerance] | [owner] |  |  | Not started

## Monitoring Calendar
Monitoring, measurement and review calendar
When each thing is measured or reviewed, by whom, what record it produces and where the result goes.
Frequency | What is measured or reviewed | Inputs | Owner | Output / record | Reported to | Next due | Status
Weekly | Canary safety test, opt-out queue, vulnerability triage | M-03, M-06, M-09 | [Creative Director] | Dashboards; triage notes | Head of AI / CTO if threshold breached | Weekly (Mondays) | Planned
Monthly | All monthly metrics collected and compared with thresholds | Metrics sheet | [Compliance Coordinator] | Updated Metrics sheet | Trust Council | [next date] | Planned
Monthly | Trust Council meeting: top risks, metrics off target, incidents, actions | Risk register; metrics | [CEO] | Minutes | Trust Council | 2026-10-21 | Planned
Monthly | ArtistMatch fairness and drift review | M-04, M-05 | [Head of AI] | Fairness report | AI Release Review | [next date] | Planned
Quarterly | Risk register review by risk owners; treatment plan progress | IMS-REG-002 | [Security Lead] | Dated register copy | Trust Council | [next date] | Planned
Quarterly | Access reviews; restore test; phishing simulation; red-team | M-07, M-11, M-14, M-15 | [Security Lead] | Review records; test reports | Trust Council | [next date] | Planned
Quarterly | Supplier and AI model-supplier check (model changes, certificates, incidents) | M-18 | [Privacy and Legal Lead] | Supplier register | Trust Council | [next date] | Planned
Twice a year | Management review (both standards) | All of the above | [CEO] | Management review minutes | Trust Council | 2026-11-18 | Planned
Yearly | Internal audit of the whole system | Audit programme | [Compliance Coordinator] | Audit report | Trust Council | AUD-2026-02 done 2026-09-19 | Done
Yearly | AIIA review of High-criticality AI systems | IMS-PRO-002 | [Head of AI] | Updated AIIAs | AI Release Review | [next date] | Planned
Yearly | Objectives reset; policy and scope review; SoA review | Objectives sheet; SoAs | [Compliance Coordinator] | Approved objectives and SoAs | Trust Council | [next date] | Planned
Yearly | Awareness training refresh for all staff and contractors | M-10 | [People and Operations Lead] | Training records | Trust Council | [next date] | Planned
Yearly | Penetration test of Canvas, Commons and API | RSK-IS-005, RSK-IS-009 | [CTO] | Pentest report | Trust Council | [next date] | Planned