## About
TWYNTRUST FRAMEWORK · Quillfen Studio
Incident and Event Log
The single log of security events, security incidents, personal-data breaches and AI incidents at Quillfen Studio, with the severity matrix, a tracker for legal and contractual notifications, and lessons learned. Used with IMS-PRO-005 Incident Management Procedure (Security and AI Incidents).
Document ID | IMS-REG-006
Version | 2.0
Prepared by | Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai
License | CC BY 4.0 — free to share and adapt, including commercially, with credit to Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai · creativecommons.org/licenses/by/4.0
Classification | Internal
Owner | [Security Lead]
Approved by | [CEO] (Trust Council)
Effective date | 2026-11-01
Kit folder | 04 Operate - Lifecycle Controls
ISO/IEC 27001:2022 | Annex A 5.24–5.28, 6.8; Clause 10.2
ISO/IEC 42001:2023 | Annex A.3.3, A.8.3, A.8.4; Clause 10.2
How to use this workbook
• | This is a SAMPLE filled in for the example company Quillfen Studio. Keep the structure, replace the example rows with your own.
• | Yellow cells are fill-in fields. Drop-down cells only accept the listed values.
• | Cells with formulas (scores, levels, due status) calculate automatically — do not type over them.
• | Log every report, even ones you close in five minutes as 'Event / near miss'. Auditors look for a living log, and trends in small events are your early warning.
• | Dates must be real dates (YYYY-MM-DD) for the 'Days open' and deadline formulas to work.
Sheets
Incident Log | One row per event or incident. Severity uses the Severity Matrix sheet. Level and Days open calculate automatically.
Severity Matrix | Same scale for security and AI incidents. Full guidance in IMS-PRO-005 Incident Management Procedure (Security and AI Incidents) section 4.
Notification Tracker | Record every notification decision — including decisions NOT to notify, with the reason. Enter 'Awareness' as a date-time; the deadline and status calculate from 'Hours allowed'.
Lessons Learned | From post-incident reviews. Actions that fix a nonconformity go to IMS-REG-008 Nonconformity, Corrective Action and Improvement Log; this sheet keeps the link.

## Incident Log
Incident and event log
One row per event or incident. Severity uses the Severity Matrix sheet. Level and Days open calculate automatically.
Incident ID | Date occurred | Date detected | Title | Type | Asset / AI system | Severity | Level | Reported by / source | Incident Lead | Personal data? | Summary | Containment and actions | Status | Date closed | Days open | Links (risks, NCs, CAs)
INC-2026-001 | 2026-01-21 | 2026-01-21 | Phishing email impersonating the payment processor sent to finance | Event / near miss | AST-010 | Low (S4) |  | Staff report | [Security Lead] | No | Two staff received a fake payout-failure email. Both reported it within 10 minutes; nobody clicked. | Sender domain blocked; warning posted; used as a phishing-simulation template. | Closed | 2026-01-22 |  | RSK-IS-002
INC-2026-002 | 2026-02-09 | 2026-02-09 | Contractor laptop stolen from a car in Lisbon | Security incident | AST-010 | Medium (S3) |  | Contractor | [Security Lead] | Possible | Company-managed laptop with full-disk encryption and passkey login stolen. | Remote lock and wipe confirmed; sessions revoked; DPO assessed: encrypted, no notification needed. | Closed | 2026-02-11 |  | RSK-IS-002
INC-2026-003 | 2026-03-04 | 2026-03-05 | ScriptMate invented a scene not in the customer's script | AI incident (model failure) | AI-SYS-002 | Low (S4) |  | Customer support | [Head of AI] | No | Shot list included a chase scene that did not exist in the script. Customer noticed before production. | Prompt template tightened to cite script line numbers; hallucination test added to the evaluation set. | Closed | 2026-03-20 |  | RSK-AI-004
INC-2026-004 | 2026-04-14 | 2026-04-14 | Staging bucket briefly public after infrastructure change | Security incident | AST-004 | Medium (S3) |  | Cloud security alert | [Platform Engineer] | No | A staging bucket holding synthetic test scripts was made public by a template error for 38 minutes. | Public access blocked; access logs show no external reads; policy-as-code rule now blocks public buckets. | Closed | 2026-04-17 |  | RSK-IS-001
INC-2026-005 | 2026-05-06 | 2026-05-06 | Artists report that ArtistMatch never shows new portfolios | AI incident (bias / fairness) | AI-SYS-003 | Medium (S3) |  | Artist complaint (12 artists) | [Head of AI] | No | Exposure ratio for new vs established artists had fallen to 0.55. Planned fairness monitoring was not running. | Exploration boost re-enabled; monthly fairness report built; NC-2026-002 raised. | Closed | 2026-06-12 |  | RSK-AI-003; NC-2026-002
INC-2026-006 | 2026-06-24 | 2026-06-24 | Foundation-model API outage — ScriptMate unavailable 3 hours | Availability / supplier | AI-SYS-002 | Medium (S3) |  | Uptime monitoring | [Platform Engineer] | No | Supplier-wide outage. Canvas worked; writing assistant showed 'paused'. | Manual mode used; status page updated; alternative-provider switch not needed (outage < RTO). See IMS-PRO-006 Business Continuity and ICT Readiness Plan. | Closed | 2026-06-24 |  | RSK-IS-004
INC-2026-007 | 2026-08-14 | 2026-08-17 | SafeFrame missed a real-person deepfake after a vendor model update | AI incident (content safety) — also a supplier issue | AI-SYS-004 | High (S2) |  | Weekly canary test set | [Head of AI] | Yes (likeness of a real person) | A customer generated a storyboard panel showing a recognisable public figure in a fabricated scene. SafeFrame's vendor had shipped a model update two days earlier that lowered its likeness-detection rate. Our weekly canary test set caught the drop 3 days later; the customer had not published the image. | Rolled SafeFrame back to the previous model version via the vendor's pinning option; added our own likeness check before image delivery; re-ran the canary set daily for 30 days; informed the customer. | Closed | 2026-09-16 |  | RSK-AI-005; NC-2026-003; CA-2026-004
INC-2026-008 | 2026-08-28 | 2026-08-28 | Image-model API key pushed to a feature branch | Security incident | AST-008 | Medium (S3) |  | Secret scanning | [Security Lead] | No | Push protection was bypassed by mistake; key visible in the private repository for 40 minutes. | Key rotated; provider logs show no misuse; bypass now needs Security Lead approval. | Closed | 2026-08-29 |  | RSK-IS-003
INC-2026-009 | 2026-09-08 | 2026-09-22 | Artist opt-out request not actioned within 14 days | AI incident (data leak) | AI-SYS-001 | Medium (S3) |  | Artist email | [Data and ML Lead] | Yes | Opt-out email went to a shared inbox that was not monitored during leave; 17 days elapsed. Artwork was not used in any training run in that period. | Request actioned; artist informed and apologised to; opt-outs now go to the consent ledger form only. | Closed | 2026-09-25 |  | RSK-AI-001; OBJ-03
INC-2026-010 | 2026-09-29 | 2026-09-29 | Prompt-injection attempts against the API to extract system prompts | Event / near miss | AI-SYS-002 | Low (S4) |  | API abuse alert | [Security Lead] | No | One trial account sent 240 injection prompts in an hour. No system prompt was returned. | Account suspended; pattern added to abuse rules. | In progress |  |  | RSK-AI-004
Formulas:
Days open = IF([Date detected]="","",IF([Date closed]="",TODAY()-[Date detected],[Date closed]-[Date detected]))

## Severity Matrix
Severity matrix and response times
Same scale for security and AI incidents. Full guidance in IMS-PRO-005 Incident Management Procedure (Security and AI Incidents) section 4.
Severity | Level | Typical criteria | Security example | AI example | Acknowledge within | Contain within | Update cadence | Who is told
Critical (S1) | Critical | Large breach of Restricted data; prohibited content delivered; full outage; attacker in production | Customer scripts bucket exfiltrated | SafeFrame fails and prohibited content reaches users | 15 minutes | 4 hours | Hourly | CEO at once; Trust Council same day
High (S2) | High | Limited breach; harmful AI output reached a customer; safety control weakened; outage > 2 h | Artist payout details exposed to another artist | SafeFrame missed a real-person deepfake after a vendor model update | 1 hour | 24 hours | Every 4 hours | CEO and both leads within 1 hour
Medium (S3) | Medium | Contained issue, no confirmed exposure; credible bias complaint; AI quality failure without serious harm | Lost encrypted laptop | ArtistMatch fairness complaint | 1 working day | 5 working days | Daily | Incident Lead and system owner
Low (S4) | Low | Event or near miss; blocked attack; single low-impact output issue | Phishing email reported, nobody clicked | Single odd shot list corrected by user | 3 working days | 30 days | On closure | Logged; monthly review

## Notification Tracker
Regulator, customer and other notifications
Record every notification decision — including decisions NOT to notify, with the reason. Enter 'Awareness' as a date-time; the deadline and status calculate from 'Hours allowed'.
Notification ID | Incident ID | Recipient | Basis (law / contract) | Required? | Awareness (date-time) | Deadline | Hours allowed | Sent at | Status | Owner | Notes
NOT-001 | INC-2026-002 | EU supervisory authority (GDPR) | GDPR Art. 33 | No | 2026-02-09 16:00 |  | 72 |  |  | [Privacy and Legal Lead] | Encrypted, wiped remotely; no risk to individuals. Decision recorded.
NOT-002 | INC-2026-004 | Affected enterprise customers | DPA clause 9 (48 h) | No | 2026-04-14 11:20 |  | 48 |  |  | [Privacy and Legal Lead] | Synthetic test data only; no customer data involved.
NOT-003 | INC-2026-006 | All Canvas customers (status page) | Service terms | Yes | 2026-06-24 08:05 |  | 1 | 2026-06-24 08:30 |  | [Creative Director] | Status page + email.
NOT-004 | INC-2026-007 | Affected customer | Customer agreement; IMS-PRO-005 s.7 | Yes | 2026-08-17 09:40 |  | 48 | 2026-08-17 15:00 |  | [Creative Director] | Customer confirmed image not published; agreed to delete it.
NOT-005 | INC-2026-007 | SafeFrame vendor | Supplier agreement | Yes | 2026-08-17 09:40 |  | 24 | 2026-08-17 11:00 |  | [Privacy and Legal Lead] | Requested written root-cause explanation (received 2026-08-25).
NOT-006 | INC-2026-007 | EU / UAE data-protection authorities | GDPR Art. 33; UAE PDPL | No | 2026-08-17 09:40 |  | 72 |  |  | [Privacy and Legal Lead] | No breach of data we hold; image labelled and unpublished. Reasoning recorded.
NOT-007 | INC-2026-007 | EU AI Act market surveillance authority | EU AI Act Art. 73 | No | 2026-08-17 09:40 |  | 360 |  |  | [Head of AI] | StoryFrame is not a high-risk AI system; Art. 73 does not apply.
NOT-008 | INC-2026-009 | Artist (data subject) | GDPR Art. 21 objection; Artist Agreement | Yes | 2026-09-22 10:00 |  | 72 | 2026-09-23 09:00 |  | [Data and ML Lead] | Confirmation of opt-out and apology sent.
NOT-009 | [INC-YYYY-NNN] | [recipient] | [law or contract] | [Yes/No] | [5 empty] | [owner] | [notes]

## Lessons Learned
Lessons learned and follow-up actions
From post-incident reviews. Actions that fix a nonconformity go to IMS-REG-008 Nonconformity, Corrective Action and Improvement Log; this sheet keeps the link.
Incident ID | What we learned | Action | Owner | Due | Status | NC / CA link
INC-2026-002 | Phishing-resistant MFA and full-disk encryption turned a theft into a non-event. | Keep device baseline; add 'stolen device' card to staff handbook. | [Security Lead] | 2026-03-15 | Done
INC-2026-003 | Evaluation set did not test for invented content. | Add hallucination cases to the release evaluation for every prompt-template change. | [Head of AI] | 2026-03-31 | Done
INC-2026-004 | Manual review of infrastructure changes missed a public-access flag. | Policy-as-code blocks public buckets in CI. | [Platform Engineer] | 2026-05-15 | Done
INC-2026-005 | Fairness monitoring in the impact assessment was never built. | Monthly fairness report; release gate checks monitoring is live. | [Head of AI] | 2026-06-30 | Done | NC-2026-002
INC-2026-007 | A supplier model change can weaken a safety control without notice; weekly canary was too slow. | Contract clause for model-change notice and version pinning; supplier AI changes added to change management; own likeness check before delivery; daily canary for 30 days. | [Privacy and Legal Lead] | 2026-11-30 | In progress | NC-2026-003; CA-2026-004
INC-2026-008 | Push-protection bypass was too easy. | Bypass requires Security Lead approval. | [Security Lead] | 2026-09-15 | Done
INC-2026-009 | Opt-outs arriving by email depend on one person's inbox. | Single opt-out form feeding the consent ledger; auto-reply points to it; ageing alert at day 7. | [Data and ML Lead] | 2026-10-31 | In progress | OBJ-03
[INC-YYYY-NNN] | [what we learned] | [action] | [owner] | [due] | Not started