## About
TWYNTRUST FRAMEWORK · Quillfen Studio
Nonconformity, Corrective Action and Improvement Log
Quillfen Studio's single log of nonconformities and corrective actions for both standards, the continual improvement register, and the record of effectiveness checks. Used with IMS-PRO-009 Nonconformity, Corrective Action and Improvement Procedure.
Document ID | IMS-REG-008
Version | 2.0
Prepared by | Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai
License | CC BY 4.0 — free to share and adapt, including commercially, with credit to Prof. Dr. Mohamed Fawzi Elgendi (Fawzooz), Fawzooz.ai · creativecommons.org/licenses/by/4.0
Classification | Internal
Owner | [Compliance Coordinator]
Approved by | [CEO] (Trust Council)
Effective date | 2026-11-01
Kit folder | 05 Prove and Improve
ISO/IEC 27001:2022 | 10.1, 10.2
ISO/IEC 42001:2023 | 10.1, 10.2
How to use this workbook
• | This is a SAMPLE filled in for the example company Quillfen Studio. Keep the structure, replace the example rows with your own.
• | Yellow cells are fill-in fields. Drop-down cells only accept the listed values.
• | Cells with formulas (scores, levels, due status) calculate automatically — do not type over them.
• | Put each nonconformity on its own row and each corrective action on a row below it, linked by 'Linked NC'. One NC can have several actions.
• | 'Due status' is a formula using TODAY(): it shows On track, Due soon (14 days or less), Overdue or Closed. Only change the 'Status' column by hand.
Sheets
NC & CA Log | Sources: audits, incidents, monitoring, management review, complaints, self-reporting. Status is set by hand; Due status calculates automatically.
Improvement Register | Opportunities for improvement (OFI) from audits and other improvement ideas (IMP) from incidents, exercises, staff and interested parties. Reviewed at every management review.
Effectiveness Checks | Defined when the action is planned; done by someone not responsible for the action. A result other than 'Effective' keeps the NC open or raises a follow-up.

## NC & CA Log
Nonconformity and corrective action log
Sources: audits, incidents, monitoring, management review, complaints, self-reporting. Status is set by hand; Due status calculates automatically.
ID | Record type | Linked NC | Date raised | Source | Grade | Requirement (27001 / 42001) | Description and evidence | Correction (immediate fix) | Root cause | Corrective action | Owner | Due date | Status | Due status | Date closed | Effectiveness check
NC-2026-001 | Nonconformity |  | 2026-05-21 | Internal audit AUD-2026-01 | Minor nonconformity | 27001 5.18 / 9.1 | Quarterly access review of production cloud accounts was not performed for Q1 2026. | Access review completed 2026-05-28; two stale roles removed. | Access review was a calendar reminder for one person with no backup and no tracking. | See CA-2026-001 | [Security Lead] | 2026-07-31 | Closed |  | 2026-07-24 | EC-01
CA-2026-001 | Corrective action | NC-2026-001 | 2026-05-28 | [6 empty] | Access reviews scheduled as recurring tickets in the compliance tracker, assigned to the Security Lead with the Platform Engineer as backup; overdue tickets reported to the Trust Council. | [Security Lead] | 2026-07-31 | Closed |  | 2026-07-24 | EC-01
NC-2026-002 | Nonconformity |  | 2026-05-12 | Incident INC-2026-005 | Minor nonconformity | 42001 9.1 / A.6.2.6 | Fairness monitoring defined in the ArtistMatch impact assessment was not running after release; the exposure ratio for new artists fell to 0.55 unnoticed. | Exploration boost re-enabled; ratio back to 0.83 by 2026-06-05. | Release sign-off did not check that the monitoring promised in the impact assessment was live. | See CA-2026-002, CA-2026-003 | [Head of AI] | 2026-07-31 | Closed |  | 2026-07-30 | EC-02, EC-03
CA-2026-002 | Corrective action | NC-2026-002 | 2026-05-19 | [6 empty] | Build a monthly ArtistMatch fairness report (exposure ratio, new vs established, by portfolio language) reviewed by the Head of AI. | [Head of AI] | 2026-06-30 | Closed |  | 2026-06-26 | EC-02
CA-2026-003 | Corrective action | NC-2026-002 | 2026-05-19 | [6 empty] | Add 'monitoring from the impact assessment is live and alerting' as a mandatory item in the AI Release Review checklist. | [Head of AI] | 2026-07-31 | Closed |  | 2026-07-30 | EC-03
NC-2026-003 | Nonconformity |  | 2026-09-19 | Internal audit AUD-2026-02 (also INC-2026-007) | Minor nonconformity | 42001 A.10.3 / 27001 5.22 | Supplier changes to SafeFrame were not assessed before going live; the supplier agreement does not require notice of model changes. | SafeFrame pinned to previous model version; own likeness check added (2026-08-17/18). | supplier onboarding checklist had no AI-model change clause. | See CA-2026-004 | [Privacy and Legal Lead] | 2026-11-30 | In progress |  |  | EC-04
CA-2026-004 | Corrective action | NC-2026-003 | 2026-10-02 | [5 empty] | supplier onboarding checklist had no AI-model change clause. | add a 'model change notification and version pinning' clause to the AI supplier contract template and to the SafeFrame agreement; add supplier model changes to the change-management trigger list. | [Privacy and Legal Lead] | 2026-11-30 | In progress |  |  | EC-04
NC-2026-004 | Nonconformity |  | 2026-09-19 | Internal audit AUD-2026-02 | Minor nonconformity | 27001 7.2 / 42001 7.2 | Two contractors who joined in July had not completed awareness training within 30 days. | Both contractors enrolled; training completed 2026-09-24. | contractor onboarding handled by hiring managers, not People Ops. | See CA-2026-005 | [People and Operations Lead] | 2026-10-31 | In progress |  |  | EC-05
CA-2026-005 | Corrective action | NC-2026-004 | 2026-10-01 | [5 empty] | contractor onboarding handled by hiring managers, not People Ops. | route all contractor onboarding through the People Ops checklist with automatic training enrolment and a day-25 reminder. | [People and Operations Lead] | 2026-10-31 | In progress |  |  | EC-05
[NC-YYYY-NNN] | Nonconformity |  | [date] | [source] | [grade] | [27001 / 42001 ref] | [what was not met, with evidence] | [immediate fix] | [root cause] | [CA ID] | [owner] |  | Open
Formulas:
Due status = IF([Status]="Closed","Closed",IF([Due date]="","",IF(TODAY()>[Due date],"Overdue",IF([Due date]-TODAY()<=14,"Due soon","On track"))))

## Improvement Register
Continual improvement register
Opportunities for improvement (OFI) from audits and other improvement ideas (IMP) from incidents, exercises, staff and interested parties. Reviewed at every management review.
ID | Date raised | Source | Improvement | Expected benefit | Clause / control | Owner | Decision | Due | Status | Outcome / notes
OFI-2026-01 | 2026-05-21 | Audit AUD-2026-01 | Link risks to assets automatically by asset ID instead of free text. | Faster risk review after asset changes | 27001 6.1.2 / 42001 6.1.2 | [Security Lead] | Adopt | 2026-08-31 | Done | Asset ID column with drop-down added to the risk register.
OFI-2026-02 | 2026-05-21 | Audit AUD-2026-01 | Collect policy acknowledgements in the HR system rather than a spreadsheet. | Reliable evidence for awareness | 27001 7.3 / 42001 7.3 | [People and Operations Lead] | Adopt | 2026-09-30 | Done | Live since September onboarding.
OFI-2026-03 | 2026-05-21 | Audit AUD-2026-01 | Give the AI Release Review template a fixed fairness and content-safety section. | Consistent release decisions | 42001 A.6.2.4, A.6.2.5 | [Head of AI] | Adopt | 2026-07-31 | Done | Merged with CA-2026-003.
OFI-2026-04 | 2026-05-21 | Audit AUD-2026-01 | Reuse a standard supplier security questionnaire. | Less effort per supplier | 27001 5.19–5.21 | [Privacy and Legal Lead] | Defer | 2027-03-31 | Not started | Deferred until supplier contract template is updated (CA-2026-004).
OFI-2026-05 | 2026-09-19 | Audit AUD-2026-02 | ArtistMatch fairness metric is reviewed monthly but not automatically alerted. | Detect fairness drift within days, not weeks | 42001 A.6.2.6 | [Head of AI] | Adopt | 2026-12-15 | In progress | Daily metric with alert below 0.8 to #trust-report; also supports OBJ-06.
IMP-2026-01 | 2026-06-18 | Tabletop BC-TT-2026-02 | Two-person rule for DNS failover written into the runbook. | Avoid false or missed failover | 27001 5.30 | [Platform Engineer] | Adopt | 2026-07-15 | Done
IMP-2026-02 | 2026-06-18 | Tabletop BC-TT-2026-02 | Status page reachable through a break-glass account when single sign-on is down. | Customer communication during outage | 27001 5.29, 5.30 | [Platform Engineer] | Adopt | 2026-07-15 | Done
IMP-2026-03 | 2026-06-18 | Tabletop BC-TT-2026-02 | Test the ScriptMate alternative model provider twice a year. | Proven AI fallback | 27001 5.30 / 42001 A.4.5 | [Head of AI] | Adopt | 2026-08-31 | Done | First switch test 2026-08-20: 40 minutes, evaluation set passed.
IMP-2026-04 | 2026-09-25 | Incident INC-2026-009 | Single opt-out form feeding the consent ledger with an ageing alert at day 7. | Meets OBJ-03 14-day target reliably | 42001 A.7.3, A.7.5 | [Data and ML Lead] | Adopt | 2026-10-31 | In progress
IMP-2026-05 | 2026-08-26 | Incident INC-2026-007 review | Evaluate a second moderation vendor to run in parallel with SafeFrame on a sample of traffic. | Independent check on a critical AI supplier | 42001 A.10.3 / 27001 5.22 | [Creative Director] | Adopt | 2027-01-31 | In progress | Linked to RSK-AI-005.
[IMP-YYYY-NN] | [date] | [source] | [idea] | [benefit] | [clause / control] | [owner] | [decision] | [due] | Not started

## Effectiveness Checks
Effectiveness checks of corrective actions
Defined when the action is planned; done by someone not responsible for the action. A result other than 'Effective' keeps the NC open or raises a follow-up.
Check ID | CA ID | NC ID | Success criterion | Planned date | Date done | Checked by | Result | Evidence | Follow-up
EC-01 | CA-2026-001 | NC-2026-001 | Q2 access review done on time with evidence; Q3 review raised on schedule | 2026-09-17 | 2026-09-17 | Contracted auditor (AUD-2026-02) | Effective | Q2 ticket closed 2026-07-08 with export of reviewed roles; Q3 ticket opened automatically 2026-09-15. | Close NC-2026-001
EC-02 | CA-2026-002 | NC-2026-002 | Monthly fairness report produced June–September and acted on | 2026-09-17 | 2026-09-17 | Contracted auditor (AUD-2026-02) | Partially effective | Reports produced every month, but the July dip to 0.76 lasted 9 days before review. | Raised OFI-2026-05 (automatic alert)
EC-03 | CA-2026-003 | NC-2026-002 | Release checklist item used for every AI release since July | 2026-09-17 | 2026-09-17 | Contracted auditor (AUD-2026-02) | Effective | 2 of 2 releases since July show the monitoring item ticked with dashboard link. | Close NC-2026-002
EC-04 | CA-2026-004 | NC-2026-003 | Clause signed with SafeFrame and foundation-model supplier; at least one vendor model change notified and assessed before going live | 2027-01-31 |  | [Head of AI] | Pending |  | Trust Council review of RSK-AI-005 acceptance on result
EC-05 | CA-2026-005 | NC-2026-004 | All contractors joining Nov–Dec 2026 complete training within 30 days | 2026-12-15 |  | Contracted auditor (AUD-2026-04) | Pending
[EC-NN] | [CA ID] | [NC ID] | [what evidence will show it worked] | [date] |  | [verifier] | Pending